## Sheet1
ECE 391 MP3 Bug Log
Date | Status | Checkpoint | Description | Resolution
2017-10-18 | Fixed | C1 | Unable to call entry from boot.S | Added padding for GDT pointer
2017-10-19 | Fixed | C1 | Compile error for IRQ wrappers in irq.S due to assembly label not recognized as function | Added .global directive, see irq.S
2017-10-19 | Fixed | C1 | Cannot use function jump table in IRQ assembly interrupt handler wrapper | The interrupt is generated by PIC, there no way for os to chose the handler
2017-10-19 | Fixed | C1 | Assertion failure in given idt_test(), causing Qemu to terminate abnormally | Missed exception 2 in Intel Manual
2017-10-20 | Fixed | C1 | Keyboard scancode prints incorrect character | Scancode is not ASCII, use PS2 keyboard mapping
2017-10-21 | Fixed | C1 | Keyboard prints two characters per key press | Scancodes > 128 are release interrupts
2017-10-21 | Fixed | C1 | RTC only sends 1 interrupt | Perform read in interrupt handler
2017-10-21 | Fixed | C1 | Pagefault after enabling paging in cr3 register | Put the initialization of page directory and table ahead of enabling paging
2017-10-21 | Fixed | C1 | Pagefault after enabling paging in cr3 register (cont) | Set page directory address aligned to 4MB
2017-10-22 | Fixed | C2 | Adjusting RTC Frequency doesn't take effect | Virtualized RTC instead
2017-10-22 | Fixed | C2 | Cannot attach file system with the module loaded in kernel | set the bootblock pointer to be extern and include the file_sys.h file in kernel.c
2017-10-22 | Fixed | C2 | the "size" of pointers with different types varies | initialize all pointers to by uint_8 and cast them into desired object ptrs when needed
2017-10-22 | Fixed | C2 | read_data cannot load the | update the read_data offset in the read_data function scope every time after calling a helper function
2017-10-22 | Fixed | C2 | When calling the read_by_name function, there is garbages pending after the file name string | the name of the file has to be stored in a char array with length of 32 bytes and always put '\0' at the end
2017-10-22 | Fixed | C2 | find some of the dentry alrways points to an empty datablock, such as directory, RTC | those object files only take a dentry in the file system without have actual data stored in datablock
2017-10-24 | Fixed | C2 | Terminal scrolling empties top line | Fixed indexing in loop over video buffer
2017-10-24 | Fixed | C2 | Command buffer backspace does not delete character from screen | putcmd now prints spaces for empty characters
2017-10-24 | Fixed | C2 | Ctrl+L clearing the screen renders video buffer unusable | Forgot to assign the ATTRIB
2017-11-01 | Fixed | C3 | Copying .elf program to 128MB fails when size > 4KB | Fixed a loop in read function of file system
2017-11-01 | Fixed | C3 | Execute iret crashes the system | Fixed a stack pointer assignment in Execute function
2017-11-02 | Fixed | C3 | Syscall always fail with general protection fault from user space | Changed privilege level of int 0x80 to allow user space
2017-11-02 | Fixed | C3 | Terminal read consistently fails due to long length | Added if statement to terminal read to shrink read size if too large
2017-11-02 | Fixed | C3 | Keyboard doesnt work on read system call | Made int 0x80 interruptible
2017-11-05 | Fixed | C3 | ls program prints everything twice | Removed printf statements from file system
2017-11-05 | Fixed | C3 | Page fault occurs occasionally | Changed page mapping for program on each execute and halt
2017-11-11 | Fixed | C3 | the file descriptor object has to be unified for OS when load file objects | has to manually create initialize operation tables according to different types of objects
2017-11-11 | Fixed | C3 | has to be able to call read/write/open/close towards different file objects | make sure that all the syscall operation functions get the same arguments under the same function name
2017-11-25 | Fixed | C4 | command line arguments have to able to copied to the given buffer in function, getargs() | first store the arguments in pcb when parsing the input string in execute()
2017-11-25 | Fixed | C4 | different pictures and terminal memories are loaded into the video memory area every time | set the *screen_start always maps to a pre-allocated memory address in virtual memory space, and change the physical memory accordingly in paging
2017-11-26 | Fixed | C4 | Pagefault in system call vidmaps | Creating new pagetable with user privilege to map video memory
2017-12-03 | Fixed | C5 | Terminal cursor incorrectly updates on Enter | Separate function for scrollup and scrollup_term
2017-12-03 | Fixed | C5 | Terminal command buffer fails on long strings | Enforce a maximum length variable for all terminals buffers
2017-12-04 | Fixed | C5 | Terminal command buffer does not produce new line on long strings | Added nl variable in lib.c to calculate the number of new lines incurred
2017-12-04 | Fixed | C5 | Switching to terminal 2 or 3 clears terminal 1's data | Used separate terminal buffers for each terminal instead
2017-12-05 | Fixed | C5 | Terminal command buffer only shows on bottom of screen | Check changes in lib.c (putcmd, putcmdend functions)
2017-12-05 | Fixed | C5 | vidmap does not work with multiple terminal | Altered page mapping for page 132+4KB depending on active process
2017-12-05 | Fixed | C5 | processes are allocated to a wrong terminal | always update the pid as the current process's parent terminal_process[] buffer before halt a process
2017-12-05 | Fixed | C5 | the interrupts generated by PIT always intervene the execution of shells | put cli() and sti() in execute() system call
2017-12-05 | Fixed | C5 | has to seperate the current running process with active terminal when calling schedule() | create two helper function in lib.c, one retures the current displaying terminal, one returns the terminal of current process
2017-12-07 | Fixed | C5 | Execute program while program in other terminal halting, then shell in other terminal not responding | put cli() and sti() in halt() system call to prevent any local interrupt
2017-12-07 | Fixed | C5 | Execute new shell when try to exit current shell | set helper function to get pid of current running program
2017-12-09 | Fixed | C5 | RTC read delay when running multiple pingpong/counter/fish | Used array of RTC locks instead of one lock
2017-12-09 | Fixed | C5 | Terminal command buffer mismatch with running process | Added term_loc variable in terminal_read